## Updated_Detailed_Task_Breakdown
Airbnb Pricing Dashboard — Detailed Task Breakdown (Updated Master Version)
Authoritative execution baseline reconciled with the PRISM project document and approved task breakdown; useful compatible items from Phase_Task_Breakdown / Key_Deliverables are incorporated.
Phase | Task ID | Task / Activity | Key Actions / Acceptance Criteria | Deliverable / Evidence | Gate
Phase 0 — Project Control & Baseline | 0.1 | Establish project baseline | Lock the PRISM Project Document, original Detailed Task Breakdown, actual source CSVs, and approved supporting Excel sheets as project references. | Project baseline register | Baseline Gate
Phase 0 — Project Control & Baseline | 0.2 | Establish project workspace | Create professional folders for source data, Power BI, documentation, QA evidence, exports, and archive. Do not alter source files. | Project folder structure
Phase 0 — Project Control & Baseline | 0.3 | Establish naming standards | Define consistent names for raw queries, clean queries, model tables, measures, columns, report pages, and documentation. | Naming standard
Phase 0 — Project Control & Baseline | 0.4 | Establish change log | Record material data, modelling, KPI, scope, and design decisions with rationale. | Change log
Phase 0 — Project Control & Baseline | 0.5 | Establish validation protocol | Define evidence required for task completion and the PASS / FIX REQUIRED / FAIL decision rule. | Validation register
Phase 1 — Project Planning (P — Problem) | 1.1 | Create project charter | Define objective, audience, scope, assumptions, dependencies and success criteria. | Project charter
Phase 1 — Project Planning (P — Problem) | 1.2 | Write business problem statement | State the Antwerp Airbnb pricing/market-analysis problem and decision need. | Approved problem statement
Phase 1 — Project Planning (P — Problem) | 1.3 | Define business questions | Define questions covering supply, pricing, availability, listing/property, hosts and reviews. | Business-question register
Phase 1 — Project Planning (P — Problem) | 1.4 | Set scope and limitations | Explicitly document descriptive/diagnostic scope and limitations: no confirmed occupancy, realised revenue, causal inference, or unsupported prediction/optimisation. | Scope and limitations statement
Phase 1 — Project Planning (P — Problem) | 1.5 | Set delivery plan | Map phases, gates, deliverables, owners and evidence requirements. | Delivery plan
Phase 1 — Project Planning (P — Problem) | 1.6 | Confirm analytical boundary | Confirm only supported measures/claims can enter the report; unavailable calendar dates are not treated as confirmed bookings. | Analytical-boundary sign-off | Scope Gate
Phase 2 — Requirements Definition (R — Requirements) | 2.1 | Identify stakeholders | Identify primary/secondary users and decision needs. | Stakeholder map
Phase 2 — Requirements Definition (R — Requirements) | 2.2 | Capture reporting requirements | Translate business questions into required metrics, dimensions, visuals and interactions. | Requirements specification
Phase 2 — Requirements Definition (R — Requirements) | 2.3 | Define KPI catalogue | Define KPI name, business definition, grain, calculation logic, format, caveats and validation method. | KPI catalogue
Phase 2 — Requirements Definition (R — Requirements) | 2.4 | Define acceptance criteria | Define measurable acceptance criteria for data, model, DAX, UX and business questions. | Acceptance checklist
Phase 2 — Requirements Definition (R — Requirements) | 2.5 | Create dashboard wireframe | Create five-page layout/wireframe before implementation. | Approved wireframes
Phase 2 — Requirements Definition (R — Requirements) | 2.6 | Define filter/interactivity matrix | Specify global/page slicers, synced slicers, cross-filtering, drill-through, tooltips, navigation and reset behaviour. | Interaction specification
Phase 2 — Requirements Definition (R — Requirements) | 2.7 | Map business questions to pages | Every approved business question must map to one or more KPI/analysis and a report page. | Requirements traceability matrix
Phase 2 — Requirements Definition (R — Requirements) | 2.8 | Define visual/KPI governance | Define formatting, titles, units, decimal precision, accessibility, and KPI presentation rules. | Visual governance standard | Requirements Gate
Phase 3 — Data Understanding & Quality (I — Investigation) | 3.1 | Inventory source files | Record file names, purpose, row count, column count, grain, refresh/date coverage and source role for listings, hosts, calendar and reviews. | Data inventory
Phase 3 — Data Understanding & Quality (I — Investigation) | 3.2 | Identify table grain | Confirm grain for each source before transformations or relationships. | Grain statement
Phase 3 — Data Understanding & Quality (I — Investigation) | 3.3 | Identify keys | Identify candidate primary/foreign keys and test uniqueness. | Key/relationship map
Phase 3 — Data Understanding & Quality (I — Investigation) | 3.4 | Profile completeness | Profile null/blank rates for important fields and document material missingness. | Completeness profile
Phase 3 — Data Understanding & Quality (I — Investigation) | 3.5 | Profile validity | Check data types, invalid ranges, invalid categories, malformed dates and other validity issues. | Validity profile
Phase 3 — Data Understanding & Quality (I — Investigation) | 3.6 | Check duplicates | Check duplicate listing_id, host_id, calendar_id, review_id and other relevant keys. | Duplicate report
Phase 3 — Data Understanding & Quality (I — Investigation) | 3.7 | Check referential integrity | Check listing/host/calendar/review key relationships and orphan records. | Integrity report
Phase 3 — Data Understanding & Quality (I — Investigation) | 3.8 | Create data-quality log | Record issue, evidence, severity, decision, treatment, impact and validation status. | Data-quality log
Phase 3 — Data Understanding & Quality (I — Investigation) | 3.9 | Profile categorical values | Profile property type, room type, neighbourhood/location and availability categories. | Category profile
Phase 3 — Data Understanding & Quality (I — Investigation) | 3.10 | Profile numeric distributions | Profile price, adjusted price, accommodates, bedrooms, minimum nights and other numeric fields. | Numeric profile
Phase 3 — Data Understanding & Quality (I — Investigation) | 3.11 | Profile date coverage | Confirm calendar/review date ranges and gaps. | Date coverage profile
Phase 3 — Data Understanding & Quality (I — Investigation) | 3.12 | Profile price outliers | Identify suspicious/extreme prices and document treatment or retention rationale. | Price outlier assessment
Phase 3 — Data Understanding & Quality (I — Investigation) | 3.13 | Establish source-to-model reconciliation baseline | Create expected counts/totals for later reconciliation through Raw → Clean → Model → DAX → Visual layers. | Reconciliation baseline | Data Quality Gate
Phase 4 — Power Query Cleaning (I — Investigation) | 4.1 | Create raw staging queries | Create Raw_Listings, Raw_Hosts, Raw_Calendar and Raw_Reviews; preserve source content and disable raw load. | Raw staging layer
Phase 4 — Power Query Cleaning (I — Investigation) | 4.2 | Create cleaned reference queries | Build clean/reference queries from raw staging; avoid unnecessary source duplication. | Clean query layer
Phase 4 — Power Query Cleaning (I — Investigation) | 4.3 | Standardise naming | Apply business-friendly names, including calendar_id and accommodates where applicable. | Standardised schema
Phase 4 — Power Query Cleaning (I — Investigation) | 4.4 | Apply data types | Set explicit types for IDs, dates, numeric, currency and categorical fields. | Typed queries
Phase 4 — Power Query Cleaning (I — Investigation) | 4.5 | Clean text fields | Trim/clean text and standardise material categorical values. | Clean dimensions
Phase 4 — Power Query Cleaning (I — Investigation) | 4.6 | Treat missing values | Apply documented, field-specific null/blank treatment; do not silently replace meaningful missingness. | Missing-value treatment log
Phase 4 — Power Query Cleaning (I — Investigation) | 4.7 | Clean prices | Validate price/adjusted price, preserve legitimate values and handle invalid/suspicious records according to the DQ decision. | Validated price fields
Phase 4 — Power Query Cleaning (I — Investigation) | 4.8 | Clean calendar status | Standardise availability values and retain the distinction between available and unavailable inventory. | Calendar status
Phase 4 — Power Query Cleaning (I — Investigation) | 4.9 | Prepare listing attributes | Prepare business-friendly listing/property attributes and appropriate derived fields such as price band where approved. | Analysis-ready listing attributes
Phase 4 — Power Query Cleaning (I — Investigation) | 4.10 | Review outliers | Apply the approved outlier treatment and document exclusions/retention. | Outlier register
Phase 4 — Power Query Cleaning (I — Investigation) | 4.11 | Validate row preservation/exclusions | Reconcile expected row counts and document every intentional exclusion/filter. | Transformation reconciliation
Phase 4 — Power Query Cleaning (I — Investigation) | 4.12 | Validate source-to-cleaned totals | Compare source and cleaned counts/totals for material fields. | Cleaning reconciliation
Phase 4 — Power Query Cleaning (I — Investigation) | 4.13 | Document Power Query steps | Document transformations and rationale for maintainability/handover. | Transformation documentation
Phase 4 — Power Query Cleaning (I — Investigation) | 4.14 | Confirm raw queries disabled from load | Verify raw queries do not unnecessarily enter the semantic model. | Raw-layer validation | Data Quality Gate
Phase 5 — Data Preparation & Semantic Model (I — Investigation) | 5.1 | Create final model tables | Create Dim_Host, Dim_Listing, Fact_Calendar and Fact_Review at validated grains. | Model-ready tables
Phase 5 — Data Preparation & Semantic Model (I — Investigation) | 5.2 | Build Date table | Create Dim_Date covering required reporting dates and mark it as the date table. | Dim_Date
Phase 5 — Data Preparation & Semantic Model (I — Investigation) | 5.3 | Create date attributes | Add year, quarter, month, month number, month-year and other approved attributes. | Date attributes
Phase 5 — Data Preparation & Semantic Model (I — Investigation) | 5.4 | Configure sorting | Set month/period sort columns to ensure chronological visuals. | Sort configuration
Phase 5 — Data Preparation & Semantic Model (I — Investigation) | 5.5 | Create relationships | Implement one-to-many relationships from dimensions to facts with appropriate filter direction. | Star schema
Phase 5 — Data Preparation & Semantic Model (I — Investigation) | 5.6 | Hide technical fields | Hide surrogate/technical keys and fields not intended for report users. | Clean field pane
Phase 5 — Data Preparation & Semantic Model (I — Investigation) | 5.7 | Create display folders | Organise measures and model fields for maintainability. | Display-folder structure
Phase 5 — Data Preparation & Semantic Model (I — Investigation) | 5.8 | Validate model | Check relationship correctness, grain, duplicates, orphan records and expected filter flow. | Model QA sign-off
Phase 5 — Data Preparation & Semantic Model (I — Investigation) | 5.9 | Validate cardinality | Confirm each relationship cardinality is supported by actual key profiling. | Cardinality validation
Phase 5 — Data Preparation & Semantic Model (I — Investigation) | 5.10 | Validate filter direction | Confirm single-direction dimension-to-fact filtering wherever possible and test for ambiguity. | Filter-flow validation
Phase 5 — Data Preparation & Semantic Model (I — Investigation) | 5.11 | Validate orphan records | Confirm no material orphan records remain without documented treatment. | Referential validation
Phase 5 — Data Preparation & Semantic Model (I — Investigation) | 5.12 | Validate date coverage | Confirm Dim_Date fully supports Fact_Calendar and Fact_Review date ranges. | Date-model validation
Phase 5 — Data Preparation & Semantic Model (I — Investigation) | 5.13 | Validate model performance basics | Review unnecessary columns, high-cardinality fields, auto date/time implications and model size basics. | Model optimisation check | Model Gate
Phase 6 — DAX & KPI Development (I — Investigation) | 6.1 | Build core count measures | Create Total Listings, Total Hosts and Total Reviews using appropriate distinct-count logic. | Core entity measures
Phase 6 — DAX & KPI Development (I — Investigation) | 6.2 | Build price measures | Create Average Nightly Price and Average Adjusted Price with documented definitions. | Pricing measures
Phase 6 — DAX & KPI Development (I — Investigation) | 6.3 | Build availability measures | Create Available Days, Unavailable Days, Total Calendar Days, Availability Rate and Unavailable Rate as supported. | Availability measures
Phase 6 — DAX & KPI Development (I — Investigation) | 6.4 | Build ratio measures | Create Reviews per Listing, Listings per Host and Average Minimum Nights where approved. | Benchmark measures
Phase 6 — DAX & KPI Development (I — Investigation) | 6.5 | Format measures | Apply consistent currency, percentage, decimal and count formatting. | Report-ready measures
Phase 6 — DAX & KPI Development (I — Investigation) | 6.6 | Validate filter context | Test measures across date, listing, host, room/property type and other relevant contexts. | DAX test results
Phase 6 — DAX & KPI Development (I — Investigation) | 6.7 | Add measure descriptions | Document each production measure's purpose and caveat. | Measure documentation
Phase 6 — DAX & KPI Development (I — Investigation) | 6.8 | Create KPI validation matrix | Record expected logic, test context, expected result and observed result for every KPI. | KPI validation matrix
Phase 6 — DAX & KPI Development (I — Investigation) | 6.9 | Validate totals against source | Reconcile KPI totals/averages against validated model/source expectations. | KPI reconciliation
Phase 6 — DAX & KPI Development (I — Investigation) | 6.10 | Validate segment/date/listing contexts | Test KPI behaviour at multiple granularities and filters to detect double counting or context errors. | Context validation | KPI Gate
Phase 7 — Exploratory Analysis (I — Investigation) | 7.1 | Analyse market supply | Analyse listing/host supply by approved dimensions. | Supply findings
Phase 7 — Exploratory Analysis (I — Investigation) | 7.2 | Analyse pricing | Analyse price levels, distributions and segment differences. | Pricing findings
Phase 7 — Exploratory Analysis (I — Investigation) | 7.3 | Analyse time patterns | Analyse monthly/period patterns for price, reviews and availability as supported. | Time-pattern findings
Phase 7 — Exploratory Analysis (I — Investigation) | 7.4 | Analyse hosts | Analyse portfolio size, host tenure and host concentration. | Host findings
Phase 7 — Exploratory Analysis (I — Investigation) | 7.5 | Analyse reviews | Analyse review activity, trends and review concentration. | Guest-engagement findings
Phase 7 — Exploratory Analysis (I — Investigation) | 7.6 | Prioritise insights | Select decision-relevant findings supported by evidence. | Insight shortlist
Phase 7 — Exploratory Analysis (I — Investigation) | 7.7 | Analyse price distribution | Assess median/percentile or distribution views where supported by the data and toolset. | Distribution findings
Phase 7 — Exploratory Analysis (I — Investigation) | 7.8 | Analyse capacity-price relationship | Assess accommodates versus price by meaningful segments. | Capacity findings
Phase 7 — Exploratory Analysis (I — Investigation) | 7.9 | Analyse bedroom-price relationship | Assess bedrooms versus price while controlling for obvious segment differences where useful. | Bedroom findings
Phase 7 — Exploratory Analysis (I — Investigation) | 7.10 | Analyse availability patterns | Assess available/unavailable patterns without interpreting unavailable as confirmed bookings. | Availability findings
Phase 7 — Exploratory Analysis (I — Investigation) | 7.11 | Assess outlier impact | Determine whether outliers materially affect KPI/visual conclusions. | Outlier findings
Phase 7 — Exploratory Analysis (I — Investigation) | 7.12 | Cross-check candidate insights | Validate that candidate insights are reproducible and not artifacts of filters, missingness or outliers. | Evidence validation | Analysis Gate
Phase 8 — Dashboard Design & Build (S — Solution) | 8.1 | Create visual theme | Define typography, colour palette, spacing, alignment, accessibility and visual-title standards. | Report theme
Phase 8 — Dashboard Design & Build (S — Solution) | 8.2 | Build Executive Overview | Create market snapshot with Total Listings, Total Hosts, Total Reviews, Average Nightly Price, Availability Rate, mix views, price trend, geographic distribution and appropriate slicers. | Page 1 — Executive Overview
Phase 8 — Dashboard Design & Build (S — Solution) | 8.3 | Build Pricing & Availability | Create price, adjusted price, availability, room/property comparisons, accommodates vs price and segment matrix. | Page 2 — Pricing & Availability
Phase 8 — Dashboard Design & Build (S — Solution) | 8.4 | Build Listing & Property Analysis | Create property/room/bedroom/accommodates analysis, price distribution, listing detail and drill-through. | Page 3 — Listing & Property Analysis
Phase 8 — Dashboard Design & Build (S — Solution) | 8.5 | Build Host Analysis | Create host count, listings per host, top hosts, location, tenure vs portfolio and host detail. | Page 4 — Host Analysis
Phase 8 — Dashboard Design & Build (S — Solution) | 8.6 | Build Review Analysis | Create total reviews, reviews per listing, review trends, top-reviewed listings, room-type analysis and detail. | Page 5 — Review Analysis
Phase 8 — Dashboard Design & Build (S — Solution) | 8.7.1 | Add page navigation | Provide consistent navigation between report pages. | Navigation evidence
Phase 8 — Dashboard Design & Build (S — Solution) | 8.7.2 | Add synced slicers | Synchronise only the slicers that should remain consistent across pages. | Synced slicer evidence
Phase 8 — Dashboard Design & Build (S — Solution) | 8.7.3 | Add reset filters | Provide a reliable reset/clear-filters mechanism where required. | Reset evidence
Phase 8 — Dashboard Design & Build (S — Solution) | 8.7.4 | Configure cross-filtering | Ensure visual interactions are intentional and do not create misleading results. | Interaction configuration
Phase 8 — Dashboard Design & Build (S — Solution) | 8.7.5 | Configure drill-through | Provide useful listing/host detail drill-through where required. | Drill-through evidence
Phase 8 — Dashboard Design & Build (S — Solution) | 8.7.6 | Configure report-page tooltips | Use tooltips to provide contextual detail without overcrowding the canvas. | Tooltip evidence
Phase 8 — Dashboard Design & Build (S — Solution) | 8.7.7 | Configure bookmarks where useful | Use bookmarks only when they improve navigation or analysis and document their purpose. | Bookmark evidence
Phase 8 — Dashboard Design & Build (S — Solution) | 8.7.8 | Add methodology/limitations note | Clearly state the availability/booking limitation and other material analytical caveats. | Methodology/limitations note
Phase 8 — Dashboard Design & Build (S — Solution) | 8.7.9 | Validate accessibility | Check contrast, readable fonts, alt text where applicable, keyboard/navigation considerations and non-colour-only meaning. | Accessibility check
Phase 8 — Dashboard Design & Build (S — Solution) | 8.7.10 | Validate visual hierarchy | Check KPI prominence, whitespace, alignment, consistency and decision flow. | UX review | Dashboard Build Gate
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.1 | Reconcile totals | Reconcile report KPIs to validated source/model expectations. | Reconciliation evidence
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.2 | Test interactions | Test slicers, cross-filtering, navigation, drill-through, tooltips and bookmarks where used. | Interaction test log
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.3 | Test usability | Review clarity, discoverability, readability and user flow. | Usability test log
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.4 | Test performance | Review refresh/model/report responsiveness and identify optimisation opportunities. | Performance check
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.5 | Conduct UAT | Execute acceptance tests against approved requirements and business questions. | UAT sign-off
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.6 | Test every KPI | Execute KPI validation matrix with evidence. | KPI QA evidence
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.7 | Test every slicer | Test each slicer for expected scope, filtering and blank behaviour. | Slicer test matrix
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.8 | Test cross-filter paths | Test intended and unintended filter paths across all pages. | Filter-flow matrix
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.9 | Test drill-through | Verify drill-through context and return/navigation behaviour. | Drill-through evidence
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.10 | Test reset functionality | Verify reset returns visuals/slicers to defined default state. | Reset test
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.11 | Test page navigation | Verify all navigation controls and page states. | Navigation test
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.12 | Test edge cases | Test zero/blank selections, small segments, extreme values and no-result contexts. | Edge-case log
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.13 | Test blank/null behaviour | Ensure blanks do not create misleading KPIs or visual errors. | Null-handling validation
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.14 | Test outlier behaviour | Confirm documented outliers behave as intended in measures and visuals. | Outlier validation
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.15 | Review performance | Optimise unnecessary visuals, columns, measures or interactions without changing approved results. | Optimisation log
Phase 9 — Testing, QA & Optimisation (S — Solution) | 9.16 | Complete requirements traceability test | Verify every approved business question is answered and every required page/KPI is represented. | Final requirements traceability | Dashboard QA Gate
Phase 10 — Insights, Publication & Handover (M — Measurement) | 10.1 | Write insight statements | Use Observation → Interpretation → Action → Caveat and ensure claims are evidence-based. | Insight summary
Phase 10 — Insights, Publication & Handover (M — Measurement) | 10.2 | Prepare recommendations | Translate supported findings into practical pricing/portfolio/market recommendations without unsupported causal claims. | Recommendation list
Phase 10 — Insights, Publication & Handover (M — Measurement) | 10.3 | Prepare final documentation | Finalise project, model, Power Query, DAX, limitations and operating documentation. | Documentation pack
Phase 10 — Insights, Publication & Handover (M — Measurement) | 10.4 | Publish report | Publish to Power BI Service only after QA/UAT pass, if publication is part of delivery. | Published report
Phase 10 — Insights, Publication & Handover (M — Measurement) | 10.5 | Configure/document refresh | Document refresh source, schedule, credentials/dependencies and operational considerations as applicable. | Refresh plan
Phase 10 — Insights, Publication & Handover (M — Measurement) | 10.6 | Complete handover | Provide PBIX, documentation, QA evidence and operational notes. | Project handover
Phase 10 — Insights, Publication & Handover (M — Measurement) | 10.7 | Create final KPI catalogue | Final KPI definitions, DAX references, formats and caveats. | Final KPI catalogue
Phase 10 — Insights, Publication & Handover (M — Measurement) | 10.8 | Create final data-quality log | Final status of all material data-quality issues and treatments. | Final DQ log
Phase 10 — Insights, Publication & Handover (M — Measurement) | 10.9 | Create dashboard walkthrough | Provide concise page-by-page explanation and usage guidance. | Dashboard walkthrough
Phase 10 — Insights, Publication & Handover (M — Measurement) | 10.10 | Create screenshots/PDF | Capture final report pages and key evidence for portfolio/review use. | Screenshots/PDF
Phase 10 — Insights, Publication & Handover (M — Measurement) | 10.11 | Create final project summary | Summarise problem, approach, model, analysis, findings, limitations and recommendations. | Final project summary
Phase 10 — Insights, Publication & Handover (M — Measurement) | 10.12 | Complete Definition-of-Done review | Confirm all approved questions are answered, data/KPIs reconcile, interactions work, limitations are visible and handover package is complete. | Final acceptance / DoD sign-off | Handover Gate
SCOPE CONTROL |  | Explicitly excluded from current implementation | Confirmed occupancy, rented days, realised revenue, revenue projection, occupancy What-If, seasonal revenue scenarios, dynamic price optimisation, causal inference and unsupported predictive claims. | Future enhancement / scope-change candidates only | Scope Lock
SCOPE CONTROL |  | Excel-plan items retained only where compatible | Dataset connectivity, cleaning, modelling, DAX, visualisation, interactivity, testing, documentation and publication are incorporated into the master WBS where they do not conflict with the approved PRISM scope. | Traceability note | Scope Lock
SCOPE CONTROL |  | Future enhancements | Actual reservation data, competitor/local-demand data, sentiment analysis, incremental refresh, scheduled publication and possible RLS may be considered only through formal scope change/future phase. | Future enhancement register | Scope Lock

## Phase_Task_Breakdown
Phase | Task Description | Subtasks | Total Hours
A. Project Kickoff & Setup | A.1 Dataset Connectivity – Connect Power BI Desktop to source files/tables (Calendar, Listings, Hosts, Reviews). | 1) Identify file formats (CSV/Excel/SQL) 2) Configure Power BI data sources (folder or database connection) 3) Verify refresh settings. | 10
B. Data Transformation & Cleaning | B.1 Power Query: Calendar Table Transformation – Clean “price” column, convert to numeric; Filter out invalid dates/rows. | Strip currency symbols/commas in “price”; Convert “available” to boolean; Handle missing “minimum_nights,” “maximum_nights”; Enforce proper date‐formats. | 10
B. Data Transformation & Cleaning | B.2 Power Query: Listings, Hosts & Reviews – Parse nested “amenities,” normalize host and review tables. | Split “amenities” into individual binary columns or a lookup table Trim/standardize text fields (“property_type,” “room_type,” etc.) Date‐format “host_since” and standardize “review_date.” | 10
C. Data Modeling & Relationships | C.1 Build Data Model – Create relationships among Calendar, Listings, Hosts, Reviews. | Identify primary/foreign keys (“listing_id,” “host_id”) Define relationships (Listings → Calendar, Hosts → Listings, Listings → Reviews) Enforce referential integrity in Power BI model view. | 15
C. Data Modeling & Relationships | C.2 Feature Aggregation (non‐ML) – Precompute aggregated review scores, host tenure, listing availability rates. | Use Power Query or DAX to compute: Average rating per listing Total number of reviews per listing Days active versus days rented Host age (current date − “host_since”).
D. DAX Calculations & Measures | D.1 Basic Measures – Create DAX measures: Total Active Days, Average Price, Availability Rate, Review Count, Host Age. | DAX for “ActiveDays” (COUNT rows where available = 1) “AvgPrice” per listing “AvailabilityRate” = ActiveDays / TotalDays “ReviewCount,” “HostAge,” “AvgRating,” etc. | 15
E. Advanced Analytics & Scenario Modeling | E.1 Parameterized What-If Scenarios (replacing ML) – Build “What-If” tables to let users adjust key drivers (occupancy %, minimum_nights, seasonal rate). | Create disconnected “What‐If” parameters (e.g., OccupancyRate, SeasonalMultiplier) Use DAX to calculate “ProjectedRevenue” and “ScenarioPrice” based on user‐selected sliders Add dynamic slicers that update key visual metrics. | 20
F. Visualization & UX Design | F.1 Design Core Report Pages – Build three key report pages: 1. Overview (Key metrics, filters) 2. Listing-Level Analysis (maps, price distribution) 3. Scenario Insights. | Page 1: KPI cards (Average Price, Avg AvailabilityRate, Total Listings, Avg OccupancyScenario); Page 2: Map (lat/long) colored by “AvgPrice”; histogram of actual “price”; Page 3: “What-If” scenario visuals (Projected Revs, scenario price distribution); Slicers: Date range, PropertyType, RoomType, “What-If” sliders. | 35
F. Visualization & UX Design | F.2 Enhance Interactivity & Tooltips – Drill-through, custom tooltips, bookmarks for storytelling. | Drill-through from a listing to detailed listing page; Custom tooltip showing host details, review metrics, occupancy scenario; Bookmarks for pre-scenario vs. post-scenario storytelling. | 10
G. Testing, QA & Optimization | G.1 Data Validation & DAX Testing – Verify that DAX measures match Power Query outputs; test “What-If” calculations. | Compare “AveragePrice” DAX vs. Power Query aggregation; Spot-check sample listings; Validate “ScenarioPrice” vs. manual calculations; Confirm data refresh doesn’t break measures. | 10
G. Testing, QA & Optimization | G.2 Performance Tuning – Optimize star schema, reduce cardinality, adjust visuals to minimize load times. | Identify high-cardinality columns; Optimize complex DAX (use VAR, minimize row-by-row iterations); Ensure visuals have page-level filters. | 5
H. Documentation & Deployment | H.1 User Guide & Technical Documentation – Write a one-page “How to Refresh & Use” guide; document data model, DAX formulas, and “What-If” steps. | User Guide: Steps to refresh data, how to use report, using “What-If” sliders; Technical Doc: Data Model diagram, DAX formulas list, Power Query M-code snippets, update “What-If” parameters instructions. | 10
H. Documentation & Deployment | H.2 Publish & Share – Publish the report to Power BI Service (workspace), configure row-level security if needed, share with stakeholders. | Upload .pbix to Power BI Service; Assign workspace permissions; Set up scheduled refresh.
I. Team Coordination & Meetings | I.1 Sprint Planning & Stand-ups – Hold a kickoff, daily stand-ups (15 min), mid-sprint review, and final demo. | Kickoff: 2h; Weekly stand-ups (1.5h); Mid-sprint review: 2h; Final demo: 2h; Retrospective: 2.5h. | 10

## Effort_Allocation
Learner | Assignments | Total Hours
L1 | A.1 Dataset Connectivity (10 h) B.1 Calendar Table Transformation (3 h) C.1 Data Model (5 h) D.1 Basic DAX Measures (5 h) I.1 Coordination (2 h) H.1 Documentation (5 h) | 30
L2 | B.2 Listings/Hosts/Reviews (7 h) C.1 Data Model (5 h) D.1 Basic DAX Measures (5 h) F.1 Visualizations (5 h) G.1 Data Validation (5 h) H.1 Documentation (3 h) I.1 Coordination (2 h) | 30
L3 | C.2 Feature Aggregation (5 h) D.1 DAX Measures (5 h) E.1 What-If Scenario Modeling (10 h) G.1 Data Validation (3 h) F.1 Visualizations (5 h) I.1 Coordination (2 h) | 30
L4 | E.1 What-If Scenario Modeling (10 h) F.1 Design Core Pages (15 h) G.2 Performance Tuning (3 h) I.1 Coordination (2 h) | 30
L5 | B.2 Listings/Hosts/Reviews (10 h) F.1 Design Core Pages (10 h) F.2 Interactivity & Tooltips (5 h) G.1 Data Validation (2 h) H.1 Documentation (2 h) I.1 Coordination (1 h) | 30

## Timeline
Week | Milestone/Deliverables
Week 1 | Kickoff (A.1 & I.1): L1 to configure all data sources, confirm connectivity Data Cleaning (B.1 & B.2): L1/L2/L5 to finish Calendar & Listings/Hosts/Reviews cleaning Initial Data Model (C.1): L1/L2/L3 validate relationships.
Week 2 | Feature Aggregation & DAX (C.2 & D.1): L1/L2/L3 finish aggregations L1/L2/L3 write all basic measures What-If Parameter Setup (E.1): L3/L4 build “What-If” tables and DAX UI Skeleton (F.1): L2/L3/L5 build first draft of Overview & Listing Analysis pages.
Week 3 | Visualization Refinement (F.1 & F.2): L2/L3/L4/L5 add interactivity/bookmarks/tooltips Testing & QA (G.1 & G.2): L2/L3/L4/L5 validate DAX, tune performance Documentation & Publish (H.1 & H.2): L1/L2/L5 finalize user guide + technical doc, publish to Power BI service Final Demo & Wrap-Up (I.1).

## Key_Deliverables
Deliverable | Details
Cleaned & Transformed Tables | Calendar_Clean (numeric price, Boolean available, valid dates) Listings_Clean (standardized text fields, split “amenities”) Hosts_Clean (valid “host_since,” calculated “HostAge”) Reviews_Clean (valid “review_date,” aggregated “ReviewCount”).
Data Model in Power BI | Star schema with relationships: Listings → Calendar (1:*) Hosts → Listings (1:*) Listings → Reviews (1:*).
DAX Measures & What-If Parameters | TotalActiveDays, AveragePrice, AvailabilityRate, ReviewCount, HostAge, AvgRating What-If tables: OccupancyRateParam, SeasonalMultiplierParam Measures: ProjectedRevenue and ScenarioPrice.
Power BI .pbix Report | Page 1: Overview (KPI cards: Avg Price Avg AvailabilityRate Total Listings ProjectedRevenue Slicers: Date range PropertyType RoomType OccupancyRate SeasonalMultiplier). Page 2: Listing Analysis (Map visual by “AveragePrice” Histogram of “price” distribution Table: Top 10 listings by ReviewCount or AvgRating). Page 3: Scenario Insights (Bar chart: “ScenarioPrice” vs. “AveragePrice” (top 20) Line chart: ProjectedRevenue vs. OccupancyRateParam Card: ProjectedRevenue Drill-through page for detailed listing view).
Documentation | User Guide PDF: Steps to refresh data how to navigate each page and use “What-If” sliders. Technical Document: Data Model diagram Full list of DAX formulas Power Query M-code snippets Instructions to update What-If parameter tables.
Published Power BI Service Workspace | .pbix uploaded to a shared workspace Row-level security configured (if required) Scheduled refresh set up Stakeholders have access.

## How_to_Use_Plan
Step | Details
Sprint Kickoff (Day 1) | L1 leads “Dataset Connectivity” Review roles/responsibilities Create shared folder (OneDrive/SharePoint) containing data files, project plan, Power BI .pbix template.
Daily Stand-ups | Each learner shares: what they completed yesterday what they plan today any blockers Use Scrum-board or Teams channel to track status.
Mid-Sprint Review (End of Week 2) | Demo: Cleaned data tables and relationships Basic DAX measures Initial What-If scenario page Collect feedback for rework.
Final Demo & Handover (End of Week 3) | Present all pages plus drill-through interaction and What-If functionality Walk through documentation Publish to Power BI Service and confirm scheduled refresh.
Retrospective | Identify what went well, what could be improved Document lessons learned in the technical doc.

## Gate_Summary
Gate | Required Exit Condition
Baseline Gate | Project references, source files, workspace, naming and validation protocol are locked.
Scope Gate | Problem, questions, scope/limitations, analytical boundary and delivery plan are approved.
Requirements Gate | Stakeholders, requirements, KPI catalogue, acceptance criteria, wireframes, interactions and governance are defined.
Data Quality Gate | Source inventory, grain, keys, completeness, validity, duplicates, integrity, outliers and quality log are validated; transformations reconcile.
Model Gate | Validated star schema, Date table, relationships, cardinality, filter direction, field organisation and model basics pass.
KPI Gate | All approved KPIs are implemented, formatted and reconciled; filter-context tests pass.
Analysis Gate | Candidate insights are evidence-backed, reproducible and consistent with limitations.
Dashboard Build Gate | Five pages, required visuals, navigation, slicers, drill-through/tooltips, limitations and accessibility pass design review.
Dashboard QA Gate | Totals, interactions, usability, performance, edge cases, KPI/slicer/filter tests and UAT pass.
Handover Gate | Insights, recommendations, documentation, KPI catalogue, DQ log, screenshots/PDF, publication/refresh notes and DoD review are complete.

## Scope_Exclusions
Excluded / Deferred Item | Reason / Rule | Status
Confirmed occupancy | Calendar unavailable status cannot distinguish bookings from host-blocked inventory. | Excluded
Rented days | Unavailable days must not be interpreted as rented/booked days. | Excluded
Realised revenue | No confirmed booking/revenue source is provided. | Excluded
Projected revenue | Would require unsupported booking/occupancy assumptions. | Excluded
Occupancy What-If parameter | Not part of approved scope and unsupported by source evidence. | Excluded
Seasonal revenue scenario | Not part of approved scope. | Excluded
Scenario price / dynamic optimisation | Not part of approved descriptive/diagnostic scope. | Excluded
Causal claims | Observational data does not establish causation. | Excluded
Predictive modelling | Current scope is descriptive/diagnostic. | Deferred
Actual reservation data | Potential future enhancement if reservation data becomes available. | Future enhancement
Competitor/local-demand data | Potential future enhancement. | Future enhancement
Sentiment analysis | Potential future enhancement if review text is formally analysed. | Future enhancement
Incremental refresh / RLS | Operational enhancements subject to deployment requirements. | Future enhancement