## Master_Task_Breakdown
Phase | PRISM | Task ID | Power BI Developer Task | Key Actions / Acceptance Criteria | Deliverable / Evidence | Gate | Status
Phase 0 — Project Control & Baseline | Control | 0.1 | Establish project baseline | Confirm approved project documents, source datasets, ERD/model baseline and task breakdown are the execution references. | Project baseline register | Baseline Gate | PASS
Phase 0 — Project Control & Baseline | Control | 0.2 | Establish practical workspace | Keep the approved repository structure; maintain clear separation between raw source data and future Power BI/clean layers without unnecessary restructuring. | Workspace baseline |  | PASS
Phase 0 — Project Control & Baseline | Control | 0.3 | Establish naming standards | Define standards for Raw_ queries, clean/model tables, measures, columns, report pages and documentation. | Naming standard |  | PASS
Phase 0 — Project Control & Baseline | Control | 0.4 | Establish change log | Record material data, modelling, KPI, scope and design decisions with rationale. | Change log |  | IN PROGRESS
Phase 0 — Project Control & Baseline | Control | 0.5 | Establish validation protocol | Define evidence required and PASS / FIX REQUIRED / FAIL decision rule. | Validation register | Phase 0 Gate | IN PROGRESS
Phase 1 — Project Planning | P | 1.1 | Create project charter | Define objective, users, business value, scope, assumptions, dependencies and success criteria. | Project charter |  | PENDING
Phase 1 — Project Planning | P | 1.2 | Define business problem | Document Antwerp Airbnb pricing, supply, availability, host and review decision need. | Approved problem statement |  | PENDING
Phase 1 — Project Planning | P | 1.3 | Define business questions | Cover market size, pricing, availability, listing/property, host and review questions. | Business-question register |  | PENDING
Phase 1 — Project Planning | P | 1.4 | Set scope and limitations | Document descriptive/diagnostic scope; unavailable dates are not confirmed bookings; no unsupported revenue/occupancy claims. | Scope and limitations statement |  | PENDING
Phase 1 — Project Planning | P | 1.5 | Set delivery plan | Map phases, gates, deliverables and evidence requirements. | Delivery plan |  | PENDING
Phase 1 — Project Planning | P | 1.6 | Confirm analytical boundary | Approve only supported KPIs and claims for the report. | Analytical-boundary sign-off | Scope Gate | PENDING
Phase 2 — Requirements Definition | R | 2.1 | Identify stakeholders | Define market manager, pricing analyst, host/operations and review/experience user needs. | Stakeholder map |  | PENDING
Phase 2 — Requirements Definition | R | 2.2 | Capture reporting requirements | Define pages, KPIs, filters, drill-through, tooltips, navigation and reset behaviour. | Requirements specification |  | PENDING
Phase 2 — Requirements Definition | R | 2.3 | Define KPI catalogue | For every KPI define business meaning, grain, formula, format, caveat and validation method. | KPI catalogue |  | PENDING
Phase 2 — Requirements Definition | R | 2.4 | Define acceptance criteria | Set data reconciliation, model, DAX, UX, accessibility and performance standards. | Acceptance checklist |  | PENDING
Phase 2 — Requirements Definition | R | 2.5 | Create dashboard wireframe | Plan five-page information architecture and visual hierarchy before building. | Page wireframes | Requirements Gate | PENDING
Phase 2 — Requirements Definition | R | 2.6 | Create traceability matrix | Map business question → KPI → visual → page → validation evidence. | Requirements traceability matrix |  | PENDING
Phase 2 — Requirements Definition | R | 2.7 | Define interaction specification | Define slicers, cross-filtering, drill-through, tooltips, navigation and reset controls. | Interaction specification |  | PENDING
Phase 3 — Data Understanding & Quality | I | 3.1 | Inventory source files | Confirm Raw_listings, Raw_hosts, Raw_calendar and Raw_reviews; document structure and source ownership. | Data inventory |  | PENDING
Phase 3 — Data Understanding & Quality | I | 3.2 | Confirm table grain | Listings one row/listing; Hosts one row/host; Calendar one row/listing-date; Reviews one row/review. | Grain statement |  | PENDING
Phase 3 — Data Understanding & Quality | I | 3.3 | Identify keys | Validate listing_id, host_id, review_id and calendar identifiers and foreign-key usage. | Key/relationship map |  | PENDING
Phase 3 — Data Understanding & Quality | I | 3.4 | Profile completeness | Assess null/blank rates for IDs, dates, prices and important categories. | Completeness profile |  | PENDING
Phase 3 — Data Understanding & Quality | I | 3.5 | Profile validity | Check dates, numeric ranges, availability, price, coordinates and category values. | Validity profile |  | PENDING
Phase 3 — Data Understanding & Quality | I | 3.6 | Check duplicates | Check duplicates according to each table's grain; do not remove legitimate calendar listing-date rows. | Duplicate report |  | PENDING
Phase 3 — Data Understanding & Quality | I | 3.7 | Check referential integrity | Validate calendar/review listing IDs against listings and listing host IDs against hosts. | Integrity exceptions |  | PENDING
Phase 3 — Data Understanding & Quality | I | 3.8 | Create data-quality log | Record issue, field, finding, treatment, rationale, impact and validation status. | Data-quality log | Data Quality Gate | PENDING
Phase 3 — Data Understanding & Quality | I | 3.9 | Profile price and availability distributions | Investigate price zeros/negatives/outliers, availability distribution and minimum/maximum nights. | Profiling evidence |  | PENDING
Phase 3 — Data Understanding & Quality | I | 3.10 | Establish reconciliation baseline | Capture source counts and totals that later cleaned/modelled results must reconcile to. | Source reconciliation baseline |  | PENDING
Phase 4 — Power Query Cleaning & Transformation | I | 4.1 | Create raw staging queries | Import four CSVs as Raw_ queries; preserve source structure and disable raw query load. | Raw staging layer |  | PENDING
Phase 4 — Power Query Cleaning & Transformation | I | 4.2 | Create clean reference queries | Reference raw queries to create clean model queries without duplicated transformation logic. | Clean query layer |  | PENDING
Phase 4 — Power Query Cleaning & Transformation | I | 4.3 | Standardise business-friendly names | Correct source naming issues such as calender_id/accomodates in clean layer while retaining traceability. | Clean field dictionary |  | PENDING
Phase 4 — Power Query Cleaning & Transformation | I | 4.4 | Apply data types | Set IDs, dates, currency/decimal, whole-number and logical/text types consistently. | Typed clean queries |  | PENDING
Phase 4 — Power Query Cleaning & Transformation | I | 4.5 | Clean text and categories | Trim/clean text, remove non-printing characters and standardise categories only after profiling. | Standardised categorical fields |  | PENDING
Phase 4 — Power Query Cleaning & Transformation | I | 4.6 | Handle missing values | Investigate relationship IDs and key fields; use null/Unspecified only with documented rationale. | Missing-value treatment evidence |  | PENDING
Phase 4 — Power Query Cleaning & Transformation | I | 4.7 | Clean price fields | Remove currency/non-numeric characters; validate negatives and investigate zero prices; document outlier approach. | Clean price fields |  | PENDING
Phase 4 — Power Query Cleaning & Transformation | I | 4.8 | Transform availability | Create readable Available/Unavailable status while retaining analytical flag and documenting the booking limitation. | Availability status |  | PENDING
Phase 4 — Power Query Cleaning & Transformation | I | 4.9 | Prepare listing attributes | Convert bedrooms/beds/accommodates appropriately; extract numeric bathroom count when reliable; validate coordinates. | Analysis-ready listing fields |  | PENDING
Phase 4 — Power Query Cleaning & Transformation | I | 4.10 | Prepare dates and review fields | Standardise calendar/review dates and validate date ranges. | Analysis-ready date fields |  | PENDING
Phase 4 — Power Query Cleaning & Transformation | I | 4.11 | Validate minimum/maximum nights | Check invalid relationships such as minimum_nights > maximum_nights and document treatment. | Nights validation evidence |  | PENDING
Phase 4 — Power Query Cleaning & Transformation | I | 4.12 | Reconcile cleaned outputs | Compare row counts, keys and material totals with baseline; document expected exclusions. | Cleaned-source reconciliation | Data Quality Gate | PENDING
Phase 5 — Data Preparation & Semantic Model | I | 5.1 | Create analysis-ready model tables | Load only final clean dimension/fact tables into the model. | Dim_Host, Dim_Listing, Fact_Calendar, Fact_Review |  | PENDING
Phase 5 — Data Preparation & Semantic Model | I | 5.2 | Create Dim_Date | Build dedicated Date table covering calendar range with required date attributes. | Dim_Date |  | PENDING
Phase 5 — Data Preparation & Semantic Model | I | 5.3 | Configure date sorting | Sort Month Name by Month Number and Weekday Name by Weekday Number; mark official date table. | Configured date table |  | PENDING
Phase 5 — Data Preparation & Semantic Model | I | 5.4 | Build star-schema relationships | Create one-to-many, single-direction relationships from dimensions to facts; resolve ambiguity deliberately. | Validated relationship model |  | PENDING
Phase 5 — Data Preparation & Semantic Model | I | 5.5 | Validate cardinality and orphan keys | Confirm relationship cardinality, filter direction and absence/handling of orphan records. | Model validation evidence |  | PENDING
Phase 5 — Data Preparation & Semantic Model | I | 5.6 | Apply semantic-model usability standards | Hide technical keys/helper fields; use display folders; set descriptions and friendly labels. | Professional semantic model | Model Gate | PENDING
Phase 6 — DAX & KPI Measure Layer | S | 6.1 | Create core market measures | Total Listings, Total Hosts, Total Reviews, Average Nightly Price, Average Adjusted Price. | Core KPI measures |  | PENDING
Phase 6 — DAX & KPI Measure Layer | S | 6.2 | Create availability measures | Available Days, Unavailable Days, Total Calendar Days, Availability Rate, Unavailable Rate. | Availability KPI measures |  | PENDING
Phase 6 — DAX & KPI Measure Layer | S | 6.3 | Create ratio measures | Reviews per Listing, Listings per Host and Average Minimum Nights. | Ratio KPI measures |  | PENDING
Phase 6 — DAX & KPI Measure Layer | S | 6.4 | Create useful derived analytical fields | Price Band, Availability Status, Host Tenure Years, Bathroom Count and Listing Display Name where appropriate. | Validated analytical fields |  | PENDING
Phase 6 — DAX & KPI Measure Layer | S | 6.5 | Apply DAX governance | Use measures for aggregations; DISTINCTCOUNT for entity metrics; appropriate currency, percentage and whole-number formats. | Formatted measure layer |  | PENDING
Phase 6 — DAX & KPI Measure Layer | S | 6.6 | Test DAX under filter context | Validate no-filter, date, category, listing and multi-filter contexts; avoid calendar-grain double counting. | DAX validation matrix | KPI Gate | PENDING
Phase 7 — Exploratory Analysis & Insight Discovery | I | 7.1 | Analyse market supply | Assess listing/host counts and property/room mix. | Supply findings |  | PENDING
Phase 7 — Exploratory Analysis & Insight Discovery | I | 7.2 | Analyse pricing patterns | Compare price by room/property type, bedrooms, capacity and time. | Pricing findings |  | PENDING
Phase 7 — Exploratory Analysis & Insight Discovery | I | 7.3 | Analyse availability patterns | Compare availability by month, weekday, room/property type and segment. | Availability findings |  | PENDING
Phase 7 — Exploratory Analysis & Insight Discovery | I | 7.4 | Analyse host portfolios | Assess portfolio size, host location and tenure patterns. | Host findings |  | PENDING
Phase 7 — Exploratory Analysis & Insight Discovery | I | 7.5 | Analyse review activity | Assess review trends, highly reviewed listings and review activity by segment. | Review findings |  | PENDING
Phase 7 — Exploratory Analysis & Insight Discovery | I | 7.6 | Prioritise evidence-based insights | Select material, explainable findings linked to business questions; document caveats. | Insight shortlist | Analysis Gate | PENDING
Phase 8 — Dashboard Design & Build | S | 8.1 | Create professional visual theme | Define typography, spacing, alignment, accessible contrast, number formats and restrained accent colour usage. | Theme standard |  | PENDING
Phase 8 — Dashboard Design & Build | S | 8.2 | Build Executive Overview | KPI cards, listing mix, price trend, map, essential filters and concise market snapshot. | Executive Overview |  | PENDING
Phase 8 — Dashboard Design & Build | S | 8.3 | Build Pricing & Availability page | Price trends, adjusted price, availability, room/property comparisons, scatter and segment matrix. | Pricing & Availability |  | PENDING
Phase 8 — Dashboard Design & Build | S | 8.4 | Build Listing & Property Analysis | Property/room analysis, bedrooms/capacity, price distribution and listing-level details. | Listing & Property Analysis |  | PENDING
Phase 8 — Dashboard Design & Build | S | 8.5 | Build Host Analysis | Host counts, listings per host, top hosts, location, tenure and host detail. | Host Analysis |  | PENDING
Phase 8 — Dashboard Design & Build | S | 8.6 | Build Review Analysis | Review totals, reviews per listing, review trend, top reviewed listings and segment analysis. | Review Analysis |  | PENDING
Phase 8 — Dashboard Design & Build | S | 8.7 | Add professional interactions | Synced slicers, page navigation, reset filters, cross-filtering, tooltips and listing drill-through. | Polished interactive UX |  | PENDING
Phase 8 — Dashboard Design & Build | S | 8.8 | Add methodology and limitations | Clearly explain source context, KPI definitions, assumptions and the availability limitation. | Transparent reporting | Dashboard QA Gate | PENDING
Phase 9 — Testing, QA & Optimisation | S | 9.1 | Reconcile dashboard totals | Validate listing, host, review and calendar totals against cleaned source. | Reconciliation evidence |  | PENDING
Phase 9 — Testing, QA & Optimisation | S | 9.2 | Validate relationships and DAX | Check filter flow and KPI values under total, segment and date-filter contexts. | Model/DAX QA log |  | PENDING
Phase 9 — Testing, QA & Optimisation | S | 9.3 | Test interactions | Test slicers, cross-filtering, drill-through, navigation, reset controls and tooltips. | Interaction test log |  | PENDING
Phase 9 — Testing, QA & Optimisation | S | 9.4 | Test usability and accessibility | Check labels, titles, contrast, readability, visual hierarchy and page purpose. | Usability/accessibility log |  | PENDING
Phase 9 — Testing, QA & Optimisation | S | 9.5 | Test edge cases and limitations | Check blanks, zero/negative price handling, outliers and availability wording. | Edge-case QA evidence |  | PENDING
Phase 9 — Testing, QA & Optimisation | S | 9.6 | Optimise performance | Remove unused columns, reduce high-cardinality burden, simplify expensive DAX/visuals and review page load. | Performance check |  | PENDING
Phase 9 — Testing, QA & Optimisation | S | 9.7 | Conduct user acceptance testing | Review against approved questions and acceptance criteria; record issues and resolutions. | UAT sign-off | Dashboard QA Gate | PENDING
Phase 10 — Insights, Publication & Handover | M | 10.1 | Write insight statements | For each finding document Observation, Interpretation, Recommended Action and Caveat. | Insight summary |  | PENDING
Phase 10 — Insights, Publication & Handover | M | 10.2 | Prepare recommendations | Prioritise actionable recommendations by business impact and evidence strength. | Recommendation list |  | PENDING
Phase 10 — Insights, Publication & Handover | M | 10.3 | Prepare final documentation | Finalise project, model, Power Query, DAX, limitations and operating documentation. | Documentation pack |  | PENDING
Phase 10 — Insights, Publication & Handover | M | 10.4 | Publish report | Publish to Power BI Service only after QA/UAT pass, if publication is required. | Published report |  | PENDING
Phase 10 — Insights, Publication & Handover | M | 10.5 | Configure/document refresh | Document source, refresh schedule, credentials/dependencies and operational considerations. | Refresh plan |  | PENDING
Phase 10 — Insights, Publication & Handover | M | 10.6 | Complete handover | Provide PBIX, documentation, QA evidence and operational notes. | Project handover |  | PENDING
Phase 10 — Insights, Publication & Handover | M | 10.7 | Create final KPI catalogue | Final KPI definitions, DAX references, formats and caveats. | Final KPI catalogue |  | PENDING
Phase 10 — Insights, Publication & Handover | M | 10.8 | Create final data-quality log | Final status of material issues and treatments. | Final DQ log |  | PENDING
Phase 10 — Insights, Publication & Handover | M | 10.9 | Create dashboard walkthrough | Concise page-by-page explanation and usage guidance. | Dashboard walkthrough |  | PENDING
Phase 10 — Insights, Publication & Handover | M | 10.10 | Create screenshots/PDF | Capture final report pages and key evidence for review/portfolio use. | Screenshots/PDF |  | PENDING
Phase 10 — Insights, Publication & Handover | M | 10.11 | Create final project summary | Summarise problem, approach, model, analysis, findings, limitations and recommendations. | Final project summary |  | PENDING
Phase 10 — Insights, Publication & Handover | M | 10.12 | Complete Definition-of-Done review | Confirm questions answered, data/KPIs reconcile, interactions work, limitations are visible and handover is complete. | Final acceptance / DoD sign-off | Handover Gate | PENDING

## Phase_Delivery_Plan
Phase | PRISM | Objective | Major Deliverables | Gate / Exit Criterion | Task Count
Phase 0 — Project Control & Baseline | Control | Establish controlled execution baseline. | Baseline register; naming standard; change log; validation register | Phase 0 control artifacts complete and approved | 5
Phase 1 — Project Planning | P | Define business problem, scope and analytical boundary. | Charter; problem statement; question register; scope statement; delivery plan | Scope and business questions approved | 6
Phase 2 — Requirements Definition | R | Translate questions into measurable report requirements. | Stakeholder map; requirements spec; KPI catalogue; acceptance criteria; wireframes; traceability; interaction spec | Requirements Gate | 7
Phase 3 — Data Understanding & Quality | I | Profile source data before final modelling. | Inventory; grain/key map; completeness/validity/duplicate/integrity profiles; DQ log; reconciliation baseline | Data Quality Gate | 10
Phase 4 — Power Query Cleaning & Transformation | I | Create trusted clean data layer. | Raw staging; clean reference queries; typed/standardised tables; price/availability/date/attribute treatments; reconciliation | Data Quality Gate | 12
Phase 5 — Data Preparation & Semantic Model | I | Build validated star-schema semantic model. | Dim_Host; Dim_Listing; Fact_Calendar; Fact_Review; Dim_Date; relationships; semantic usability | Model Gate | 6
Phase 6 — DAX & KPI Measure Layer | S | Build governed, filter-responsive KPI layer. | Core market KPIs; availability KPIs; ratios; derived analytical fields; formatted measures; validation matrix | KPI Gate | 6
Phase 7 — Exploratory Analysis & Insight Discovery | I | Discover evidence-based business findings before final dashboarding. | Supply; pricing; availability; host; review findings; insight shortlist | Analysis Gate | 6
Phase 8 — Dashboard Design & Build | S | Build professional five-page interactive report. | Theme; Executive Overview; Pricing & Availability; Listing & Property; Host; Review; interactions; methodology | Dashboard QA Gate | 8
Phase 9 — Testing, QA & Optimisation | S | Validate data, model, DAX, UX and performance. | Reconciliation; model/DAX QA; interaction; accessibility; edge cases; performance; UAT | Dashboard QA Gate | 7
Phase 10 — Insights, Publication & Handover | M | Communicate findings and deliver a maintainable product. | Insights; recommendations; documentation; publication; refresh; handover; KPI/DQ catalogue; walkthrough; screenshots; summary; DoD | Handover Gate | 12

## Final_Deliverables
Deliverable | Included | Produced In | Professional Completion Standard
Cleaned & Transformed Power Query layer | YES | Phase 4 | Raw staging preserved; clean reference queries; documented transformations; reconciliation evidence.
Power BI Star-Schema Semantic Model | YES | Phase 5 | Validated grain, keys, relationships, cardinality, filter direction, date table and semantic usability.
DAX KPI / Measure Layer | YES | Phase 6 | Governed measures, correct filter context, formats, descriptions and validation evidence.
Five-page Power BI .pbix report | YES | Phase 8 | Executive Overview; Pricing & Availability; Listing & Property; Host; Review Analysis.
Interactive UX | YES | Phase 8 | Synced slicers, navigation, reset filters, cross-filtering, tooltips and drill-through.
Data Quality Log | YES | Phases 3–4, finalised 10.8 | Material issues, decisions, rationale, impact and final status.
KPI Catalogue | YES | Phase 2, finalised 10.7 | Definition, formula, grain, format, caveat and validation method.
QA / Validation Evidence | YES | Phase 9 | Reconciliation, DAX, model, interaction, usability, accessibility, edge-case and performance tests.
Insights & Recommendations | YES | Phase 10 | Observation, interpretation, action and caveat; evidence-based.
PRISM Project Documentation | YES | Phase 10 | Problem, requirements, investigation, solution, measurement and limitations.
Dashboard screenshots / PDF | YES | Phase 10 | Final pages captured for assessment/portfolio evidence.
Power BI Service publication | CONDITIONAL | Phase 10 | Only after QA/UAT; workspace, refresh and access documented as applicable.
What-If occupancy/revenue scenario modelling | NO — OUT OF SCOPE | Scope Control | Not implemented because the approved analytical boundary does not support confirmed occupancy, realised/projected revenue or dynamic price optimisation.
Predictive modelling / price optimisation | NO — OUT OF SCOPE | Scope Control | Future enhancement only unless formally re-scoped with appropriate data/methodology.

## Execution_Rules
Type | Rule | Implementation
Rule | Power BI-only implementation | Use Power BI Desktop, Power Query and DAX for dashboard implementation.
Rule | No Python | No Python/Pandas or external Python data-processing scripts.
Rule | No Git activity without explicit user instruction | Do not perform or instruct Git/GitHub activity unless explicitly requested.
Gate rule | No phase skipping | Do not move to the next phase until current phase is validated and approved.
Task rule | Evidence before PASS | A task is PASS only after evidence is supplied and reviewed.
Data rule | Source preservation | Keep raw CSV source data unchanged; clean through Power Query.
Analytical rule | Availability limitation | Unavailable calendar dates are not treated as confirmed bookings/occupancy.
Analytical rule | Revenue limitation | Do not claim realised or confirmed revenue from calendar availability.
DAX rule | Measure governance | Use measures for aggregations and validate under relevant filter contexts.
Model rule | Star schema | Prefer one-to-many, single-direction dimension-to-fact relationships.
UX rule | Accessibility | Use readable labels, contrast, spacing, consistent formats and clear visual titles.
QA rule | Definition of Done | All approved business questions answered; data/KPIs reconcile; interactions work; limitations visible; handover complete.

## Scope_Control
Scope | Item | Decision / Reason
In Scope | Pricing | Average/adjusted listed price analysis and segmentation.
In Scope | Availability | Available/Unavailable days and rates; clearly not occupancy.
In Scope | Listings | Property, room type, bedrooms, capacity, geography and listing detail.
In Scope | Hosts | Host portfolio, location, tenure and listings per host.
In Scope | Reviews | Review count/activity, trends and listing/segment analysis.
In Scope | Descriptive & diagnostic analytics | Evidence-based comparisons and recommendations.
Out of Scope | Confirmed occupancy | Requires reservation/booking source.
Out of Scope | Realised revenue | Requires transaction/reservation data.
Out of Scope | Projected revenue / occupancy What-If | Excluded by approved analytical boundary.
Out of Scope | Dynamic price optimisation / prediction | Future enhancement unless formally re-scoped.

## README
Item | Value
Project | Airbnb Pricing Dashboard — Antwerp Market Analysis
Tool | Microsoft Power BI Desktop / Power Query / DAX
Framework | PRISM — Problem, Requirements, Investigation, Solution, Measurement
Purpose | Professional Power BI delivery plan combining the approved master WBS with compatible deliverables from the original plan.
Authoritative execution basis | Updated Detailed Task Breakdown + PRISM Project Document + approved scope controls.
Implementation boundary | Power BI dashboard only; no Python and no Git activity unless explicitly requested.
Gate discipline | Evidence → validation → PASS → next task. Phase gate approval required before next phase.
Scenario decision | Occupancy/revenue What-If and optimisation are explicitly excluded from the current approved scope.